## Tabelle1
UC Name | Time spent | FP
register | 14:30 | 23.3
login | 11:30 | 13.8
logout | 11:25 | 3.2
edit user profile | 8:30 | 8.5
delete user profile | 7:00 | 7
Use Case | Estimated (h) | Logged (h) | Transaction | [5 empty] | Function Points
|  |  |  | DET | RET | FTR | Complexity | Number of
Register | 11 | 14.5 | Inputs | 6 | x | 1 | 0 | 1 | 23.32
|  |  | Outputs | 0 | x | 0 | 0 | 0
|  |  | Inquiries | 2 | x | 1 | 0 | 1
|  |  | Logical Files | 5 | 2 | x | 0 | 1
|  |  | External Interface | 1 | 1 | x | 0 | 1
Login | 8 | 11.5 | Inputs | 3 | x | 1 | 0 | 1 | 13.78 |  |  | Time spent on
|  |  | Outputs | 0 | x | 0 | 0 | 0 |  | System | Use Case | General | Documentation | Coding | Testing | Total
|  |  | Inquiries | 1 | x | 1 | 0 | 1 |  | login system | register | 2.5 | 3 | 8 | 1 | 14.5
|  |  | Logical Files | 2 | 1 | x | 0 | 1 |  |  | login | 2 | 2.5 | 6.5 | 0.5 | 11.5
|  |  | External Interface | 0 | 0 | x | 0 | 0 |  |  | logout | 1.5 | 2 | 6 | 0.8 | 10.3
Logout | 8 | 11.3 | Inputs | 1 | x | 1 | 0 | 1 | 3.18 | interact with meets | view meets |  |  |  |  | 0
|  |  | Outputs | 0 | x | 0 | 0 | 0 |  |  | create meets |  |  |  |  | 0
|  |  | Inquiries | 0 | x | 1 | 0 | 0 |  |  | joins meets |  |  |  |  | 0
|  |  | Logical Files | 0 | 0 | x | 0 | 0 |  |  | leave meets |  |  |  |  | 0
|  |  | External Interface | 0 | 0 | x | 0 | 0 |  |  | comment on meets |  |  |  |  | 0
View meets | xx | xx | Inputs | 4 | x | 1 | 0 | 1 | 56.18 | user system | edit own user profile | 1.3 | 2.,5 | 7.2 | 0.9 | 8.5
|  |  | Outputs | 6 | x | 1 | 0 | 1 |  |  | delete own profile | 0.5 | 1.5 | 5.5 | 0.8 | 7
|  |  | Inquiries | 1 | x | 1 | 0 | 1 |  |  | view user profile |  |  |  |  | 0
|  |  | Logical Files | 2 | 1 | x | 0 | 1 |  |  | send friendship requests |  |  |  |  | 0
|  |  | External Interface | 0 | 0 | x | 0 | 0 |  |  | accept friendship requests |  |  |  |  | 0
Create meets | xx | xx | Inputs | 9 | x | 1 | 0 | 1 | 66.78 |  | friend list |  |  |  |  | 0
|  |  | Outputs | 0 | x | 0 | 0 | 0 |  | administrate meets | accept users |  |  |  |  | 0
|  |  | Inquiries | 1 | x | 1 | 0 | 1 |  |  | decline users |  |  |  |  | 0
|  |  | Logical Files | 4 | 2 | x | 0 | 2 |  |  | kick users |  |  |  |  | 0
|  |  | External Interface | 1 | 1 | x | 0 | 1 |  | manipulating meets | delete own meets |  |  |  |  | 0
Join meets | xx | xx | Inputs | 1 | x | 1 | 0 | 1 | 21.20 |  | edit own meets |  |  |  |  | 0
|  |  | Outputs | 0 | x | 0 | 0 | 0
|  |  | Inquiries | 1 | x | 1 | 0 | 1
|  |  | Logical Files | 2 | 1 | x | 0 | 1 |  | WIRD FÜR DIE AUTO. „Complexity“-BERECHNUNG BENÖTIGT
|  |  | External Interface | 0 | 0 | x | 0 | 0
Leave meets | xx | xx | Inputs | 1 | x | 1 | 0 | 1 | 21.20
|  |  | Outputs | 0 | x | 0 | 0 | 0
|  |  | Inquiries | 1 | x | 1 | 0 | 1
|  |  | Logical Files | 2 | 1 | x | 0 | 1
|  |  | External Interface | 0 | 0 | x | 0 | 0 |  | EI | DETS
Comment on meets | xx | xx | Inputs | 2 | x | 1 | 0 | 1 | 28.62 | FTR | 5 | 16 | 17
|  |  | Outputs | 1 | x | 1 | 0 | 1 |  | 2 | Low | Low | Avg
|  |  | Inquiries | 1 | x | 1 | 0 | 1 |  | 3 | Low | Avg | High
|  |  | Logical Files | 2 | 1 | x | 0 | 1 |  | 4 | Avg | High | High
|  |  | External Interface | 0 | 0 | x | 0 | 0
Edit own user profile | 12 | 8.5 | Inputs | 6 | x | 1 | 0 | 1 | 37.1 | EO + EQ | DETS
|  |  | Outputs | 0 | x | 0 | 0 | 0 |  | FTR | 6 | 20 | 21
|  |  | Inquiries | 1 | x | 1 | 0 | 1 |  | 2 | Low | Low | Avg
|  |  | Logical Files | 2 | 1 | x | 0 | 1 |  | 4 | Low | Avg | High
|  |  | External Interface | 0 | 0 | x | 0 | 0 |  | 5 | Avg | High | High
Delete own profile | 10 | 7 | Inputs | 6 | x | 1 | 0 | 0 | 270.4
|  |  | Outputs | 0 | x | 0 | 0 | 0 |  | ILF + ELF | DETS
|  |  | Inquiries | 2 | x | 5 | 0 | 1 |  | RETS | 20 | 51 | 52
|  |  | Logical Files | 26 | 7 | x | 0 | 4 |  | 2 | Low | Low | Avg
|  |  | External Interface | 0 | 0 | x | 0 | 0 |  | 6 | Low | Avg | High
View user profile | xx | xx | Inputs | 1 | x | 1 | 0 | 0 | 15.6 | 7 | Avg | High | High
|  |  | Outputs | 1 | x | 1 | 0 | 0
|  |  | Inquiries | 1 | x | 1 | 0 | 1
|  |  | Logical Files | 2 | 1 | x | 0 | 1 |  | Inputs |  | EI
|  |  | External Interface | 0 | 0 | x | 0 | 0 |  | Outputs |  | EO
Send friendship requests | xx | xx | Inputs | 0 | x | 0 | 0 | 0 | 11.6 | Inquiries |  | EQ
|  |  | Outputs | 0 | x | 0 | 0 | 0 |  | Logical Files |  | ILF
|  |  | Inquiries | 1 | x | 1 | 0 | 1 |  | External Interface |  | ELF
|  |  | Logical Files | 2 | 1 | x | 0 | 1
|  |  | External Interface | 0 | 0 | x | 0 | 0
Accept friendship requests | xx | xx | Inputs | 1 | x | 1 | 0 | 0 | 11.6
|  |  | Outputs | 0 | x | 0 | 0 | 0
|  |  | Inquiries | 1 | x | 1 | 0 | 1
|  |  | Logical Files | 2 | 1 | x | 0 | 1
|  |  | External Interface | 0 | 0 | x | 0 | 0
Friend list | xx | xx | Inputs | 1 | x | 1 | 0 | 0 | 11.6
|  |  | Outputs | 0 | x | 0 | 0 | 0
|  |  | Inquiries | 1 | x | 1 | 0 | 1
|  |  | Logical Files | 2 | 1 | x | 0 | 1
|  |  | External Interface | 0 | 0 | x | 0 | 0
Accept users | xx | xx | Inputs | 1 | x | 1 | 0 | 0 | 11.6
|  |  | Outputs | 0 | x | 0 | 0 | 0
|  |  | Inquiries | 1 | x | 1 | 0 | 1
|  |  | Logical Files | 2 | 1 | x | 0 | 1
|  |  | External Interface | 0 | 0 | x | 0 | 0
Decline users | xx | xx | Inputs | 1 | x | 1 | 0 | 0 | 11.6
|  |  | Outputs | 0 | x | 0 | 0 | 0
|  |  | Inquiries | 1 | x | 1 | 0 | 1
|  |  | Logical Files | 2 | 1 | x | 0 | 1
|  |  | External Interface | 0 | 0 | x | 0 | 0
Kick users | xx | xx | Inputs | 1 | x | 1 | 0 | 0 | 11.6
|  |  | Outputs | 0 | x | 0 | 0 | 0
|  |  | Inquiries | 1 | x | 1 | 0 | 1
|  |  | Logical Files | 2 | 1 | x | 0 | 1
|  |  | External Interface | 0 | 0 | x | 0 | 0
Delete own meets | xx | xx | Inputs | 1 | x | 1 | 0 | 0 | 58.5
|  |  | Outputs | 0 | x | 0 | 0 | 0
|  |  | Inquiries | 2 | x | 1 | 0 | 1
|  |  | Logical Files | 12 | 2 | x | 0 | 2
|  |  | External Interface | 0 | 0 | x | 0 | 0
Edit own meets | xx | xx | Inputs | 9 | x | 1 | 0 | 1 | 37.7
|  |  | Outputs | 0 | x | 0 | 0 | 0
|  |  | Inquiries | 1 | x | 1 | 0 | 1
|  |  | Logical Files | 4 | 2 | x | 0 | 1
|  |  | External Interface | 0 | 0 | x | 0 | 0