## Risks
Risk dimension	Probability of Occurrence	Impact	Risk factor	Risk mitigation	Person in Charge of Tracking
poor productivity	45%	50%	22,5	emphasize deadlines and motivate colleagues to work	Andreas Riepl
framework capabilities do not match desired features	60%	35%	21	if framework does not support features the team will have to implement the components by hand	Luca Carotenuto
Miscommunication & Misunderstandings	25%	80%	20	weekly updates, synch regularly via messenger	Luca Carotenuto
team member gets sick	20%	80%	16	no alcohol abuse, healthy nutrition	entire team
unrealistic time schedule	80%	20%	16	unrealistic time schedules can be mitigated by spending more effort on time management and time planning	Sebastian Luther
architecture lacks flexibility	25%	55%	13,75	choose approriate architecture that supports	Sebastian Luther
Server issues	15%	90%	13,5	little influence on the server environment (Steven Kovacs)	Andreas Riepl
lack of knowledge or loss of knowledge after semester break for specific technologies	70%	15%	10,5	ask people around who might have knowledge or relearn technologies	entire team
team member is fired from company / exmatriculated	5%	95%	4,75	improve performance at university/work	entire team